## Sheet1
Staff | Code | Housing
Geoff | 1 | Off
Delaney | 2 | Rm1
Post doc or Lily | 3 | Rm2
USM | 4 | Rm3
Seth | 5 | Rm3
Sarah | 6 | Rm4
Stacie | 7 | Rm4
Guest |  | Rm 5
Staff/Scientists |  | Rm 6
Task | Who | April |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
|  | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
order sensors | Ian/Nick | bar: April week 4
order lysimeters | John | bar: April week 4
order soil resp collars | Tim | bar: April week 4
Site Selection | 1,5 | April week 1: 1,5; May week 2: 1,5
Plot Lay Out | 1,5 | May week 3: 1,5; May week 4: 1,5
Vegetation Survey | 2 | May week 1: 2; June week 2: 2; June week 3: 2
Install sensors (120) | 1,4 | May week 1: 1,4; June week 2: 1,4; June week 3: 1,4; June week 4: 1,4
Install lysimeters (40) | 3,5 | May week 1: 3,5; June week 2: 3,5; June week 3: 3,5
Install resp collars | Cornell + 1 | May week 1: 6; June week 3: 6
Install root cores | Cornell + 1 | May week 1: 7; June week 3: 7
Install trace gas collars | IES + 1 | May week 1: 6; June week 3: 6
Hemispheric Photos | 2 | June week 1: 2; July week 3: 2; July week 4: 2
Foliage Sampling | 2 | bar: July week 4 to July week 1
Coarse Woody Debris Plotss | bar: October week 3 to October week 4
Litterfall Collections | 1 | bar: August week 1 to October week 4
Wounding |  | July week 4: 2; July week 1: 2
Litterbags | 1 | bar: October week 1 to November week 4
soil solution collections | 3 | June week 1: 3; July week 3: 3; July week 1: 3; August week 3: 3
respiration collections | 1 | bar: June week 1; July week 3; July week 1; August week 3
trace Gas Collections
N Mineralization
root collections | Cornell + 1 | bar: October week 1
Icing trials |  | June week 4: 2,3; July week 1: 1,2,3; August week 2: 1,2,3
Ornaments | bar: August week 1 to September week 4
data, presentatons | 1,2,3,4,5,6,7 | June week 1: 1,2,3,4; July week 2: 1,2,3,4,5,6,7
Resampling Plots | 6,7 | May week 1: 6,7; June week 2: 6,7; June week 3: 6,7; June week 4: 6,7; June week 1: 6,7; July week 3: 6,7; July week 4: 6,7; July week 1: 6,7; August week 2: 6,7; August week 3: 6,7; August week 1: 7; September week 2: 7; September week 3: 7; September week 4: 7
??