## Sheet1
Staff | Code | Housing
Geoff | 1 | Off
Delaney | 2 | Rm1
Lily | 3 | Rm1
Jaren | 4 | Rm2
Chelsea | 5 | Rm3
Sarah | 6 | Rm4
Stacie | 7 | Rm4
Post Doc | 8 | Rm2
Other | 9 | Rm5
Staff/Scientists |  | Rm 6
(number are SUGGESTED Doers)
Task | Who | April |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
|  | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | Meetings | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
order sensors | Ian/Nick | XX
order lysimeters | John | XX
order soil resp collars | Tim | XX
Site Selection | 1,5 |  | 1,5 | 1,5
Plot Lay Out | 1,5 |  |  |  | 1,5 | 1,5
Vegetation Survey | 2
Install sensors (120) | 1,4 | [5 empty] | 1,4 | 1,4 | 1,4 | 1,4 | 2 |  | week 3: 2; week 4: 2
Install lysimeters (40) | 3,5 | [5 empty] | 3,2 | 3,2 | 3,2
Soil samples
Install resp collars | Cornell + 1 | [5 empty] | 1 |  | 1
Install root cores | Cornell + 2 | [5 empty] | 5,9 | 5,9 | 5,9
Install trace gas collars | IES + 1
Hemispheric Photos | 2 | [9 empty] | 2 |  | week 3: 2; week 4: 2
Foliage Sampling | 2 | bar: week 4 to week 1
Coarse Woody Debris Plotss | bar: October week 3 to October week 4
Litterfall Collections | 1 | bar: August week 1 to October week 4
Wounding | [12 empty] | week 4: 2; week 1: 2
Litterbags | 1 | bar: October week 1 to November week 4
soil solution collections | 3 | [9 empty] | 3 |  | week 3: 3; week 1: 3; August week 3: 3
respiration collections | 1 | [9 empty] | 1 | bar: week 3; week 1; August week 3
trace Gas Collections
N Mineralization
root collections | Cornell + 1 | bar: October week 1
Icing trials | [9 empty] | 2,3 |  |  | week 1: 1,2,3; August week 2: 1,2,3
Ornaments | bar: August week 1 to September week 4
data, presentatons | 1,2,3,4,5,6,7 | [9 empty] | 1,2,3,4 | 1,2,3,4,5,6,7
Resampling Plots | 6,7 |  |  |  |  | 6,7 | 6,7 | 6,7 | 6,7 | 6,7 | 6,7 |  | week 3: 6,7; week 4: 6,7; week 1: 6,7; August week 2: 6,7; August week 3: 6,7; August week 1: 7; September week 2: 7; September week 3: 7; September week 4: 7
??