## Sheet1
(number are SUGGESTED Doers)
Task | Who | April |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
|  | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | Meetings | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
order sensors | Ian/Nick | XX
order lysimeters | John | XX
order soil resp collars | Tim | XX
Site Selection |  |  | XX | XX
Plot Lay Out |  |  |  |  | XX | XX
Vegetation Survey | [6 empty] | XX | XX | XX | XX
Install sensors (120) | bar: week 1 to August week 3
Install lysimeters (40) | bar: week 3 to week 4
Soil samples | bar: week 1 to August week 3
Install resp collars | Cornell + 1 | [5 empty] | XX
Install root cores | Cornell + 2 | [5 empty] | XX | bar: September week 1 to October week 3
Install trace gas collars | IES + 1 | [5 empty] | XX | bar: September week 4; October week 3
Hemispheric Photos | 2 | bar: August week 4
LAI | bar: August week 4
Foliage Sampling | Paul +3 | bar: week 1
Coarse Woody Debris Plots | bar: October week 3 to October week 4
Litterfall Collections | 1 | bar: week 4; August week 1; September week 3; September week 1; October week 3; October week 1
Wounding
Litterbags | 1 | bar: week 1 to August week 2; October week 1 to November week 4
soil solution collections | 3 | bar: week 4 to August week 2; August week 1
respiration collections | 1 | [5 empty] | XX |  | XX |  | XX | bar: week 3; August week 2; August week 1
trace Gas Collections | bar: August week 4
N Mineralization | bar: August week 3
root collections | Cornell + 1 | bar: October week 1
Icing trials | bar: August week 3
Ornaments | [10 empty] | X | bar: August week 2; August week 1 to September week 4
data, presentatons | 1,2,3,4,5,6,7 | [9 empty] | XXXX | XXXX
Resampling Plots | 6,7 |  |  |  |  | XX | XX | XX | XX | XX | XX | bar: week 3 to August week 3; August week 1 to September week 4
Photography | bar: week 1 to August week 1