## Sheet1
Task | Person Hours | Total Summer Person Days |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  | Comments
|  |  | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | Meetings | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
Vegetation Survey | 2 People 6 Days + Amey | 12 |  |  |  |  | 10 | 2
GPS Plot Corners |  | 5 | 5
TSR collections | 2 People 1.5 days | 42 | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | week 3: 3; week 1: 3; August week 3: 3; August week 1: 3; September week 3: 3; September week 1: 3; October week 3: 3; October week 1: 3; November week 3: 3 | Shoestring?
Cooperators MtgPresentations |  | 10 | [8 empty] | 5 | 5
Lysimeters | 2 People .5 days | 16 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | bar: week 4; August week 2; August week 4; September week 2; September week 4; October week 2; October week 4; November week 2; November week 4; December week 2; December week 4
Hemispheric Photos/LAI | 3 People 2 days | 12 | [10 empty] | week 3: 6; December week 2: 6
Foliage Sampling | 2 People 2 days | 4 | [10 empty] | week 4: 4
N Mineralization | 2 People 2 days | 20 |  | 4 | [6 empty] | 4 |  | August week 2: 4; September week 4: 4; November week 2: 4
Trace Gas Collections | 2 People 2 days | 8 |  |  | 4 | [7 empty] | November week 3: 4
Root Collections | 4 people 2 days | 8 | [10 empty] | October week 4: 8
Litterfall Collections | 1 person 1 days | 8 |  |  |  | 1 | bar: August week 3; August week 1; September week 3; September week 1; October week 3; October week 1; November week 3
CWD Intersect | 3 People 3 days | 18 | [5 empty] | 9 |  |  |  |  | November week 3: 9
CWD Plot Removal | 3 People 5 days | 60 | [6 empty] | 15 | 15 |  |  | November week 4: 15; November week 1: 15
Litterbags | 1 person 2 days | 4 | 2 | [9 empty] | November week 4: 2
LiDar | As needed | 2 | bar: August week 4; October week 2
Bugs + Birds | As needed | 0 | [32 empty] | Wendy's Project, let her fill in timing
REU Supervision | 1 Day per week | 10 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | Wendy's Project, let her fill in timing | bar: week 3 to week 1
| Total | 239 | 10 | 5 | 7 | 3 | 14 | 13 | 19 | 17 | 13 | 7 | 10 | 6 | 4 | 5 | 4 | 2 | 4 | 1 | 4 | 5 | 4 | 2 | 4 | 9 | 4 | 5 | 17 | 18 | 15 | 7 | 0 | 1
1 full time tech May through December (days) | 160
Additional Tech needed (days) | 79
Root Cores and Sorting | $5000 to Geoff Wilson