## Vertical
Colors: | Meeting |  | Burn | Upload |  | Product Generation | [7 empty] | last edited 6/3/10
Date | Time UTC | Time (ET) | Dur | Actionee | Posted on SFTP | Action | OP31117_A Step | Altitude | AUS View | AK View | HAW view | APL View | Location Reqs | Comments | Needed in addition to OP31117_A
2010-11-03 |  | 8:30 | 2d |  |  | IBEX Extended Mission TIM
2011-02-15 | [5 empty] | Orbit In The Life Testing Begins
2011-03-16 |  | 9:00 | 2.5d |  |  | IBEX Pre-Maneuver TIM
2011-03-29 | [5 empty] | Diagnostic - Hi Gain | [6 empty] | 30re asc
2011-04-06 | [5 empty] | Diagnostic - Lo Gain | [6 empty] | in magnetosheath
2011-04-07 | [5 empty] | Individual Procedure Walkthough | [7 empty] | Bret FlatSat manager Walkthrough of procedures by the subsystem/system engineer responsible - Orbital & FDG seperately
2011-04-20 | [5 empty] | Diagnostic - Star Tracker Image Dump | [6 empty] | Housekeeping State >=40ksps
2011-04-20 | [5 empty] | SWT - Science Team Decision on Pointing | [7 empty] | Point at sun 2.5d prior to apogee, 2.5d prior to perigee
2011-04-28 | [5 empty] | Diagnostic - Gyro Test Diagnostic - 22N Cat Bed Heater Test Diagnostic - CSD Table Dump | [6 empty] | Housekeeping State >=40ksps |  | OP31205, OP31206
2011-05-02 |  | 9:00 | 2d |  |  | Combined Procedure Walkthrough #1 | [7 empty] | FDG + Orbital walkthrough @ Orbital
2011-05-18 |  | 8:30 | 2.5d |  |  | Combined Procedure Walkthrough #2 | [7 empty] | FDG + Orbital walkthrough @ Orbital; anomalies
2011-05-31 | [5 empty] | Orbit in the Life Testing Completed
2011-06-01 | 1045 | 6:45 | 35m |  |  | Contact AOS : HAW01, 2k |  | 47a
| 1120 | 7:20 |  |  |  | Contact LOS : HAW01
2011-06-01 | 1300 | 9:00 | 2h |  |  | Pre-Spin Up MAC
2011-06-01 | 1320 |  |  |  |  | Apogee |  | 47
2011-06-03 | 1100 | 7:00 | 35m |  |  | Contact AOS : HAW01, 2k |  | 41d
| 1135 | 7:35 |  |  |  | Contact LOS : HAW01
2011-06-05 | 0402 |  |  |  |  | AK View begin
2011-06-05 | 0430 | 0:30 | 35m |  |  | Contact AOS : AK,2k |  | 8d
|  |  | 25m |  |  | SSR Dump (if data rate allows)
|  |  | 1m |  |  | Verify in Housekeeping | 2 | [6 empty] | Can be done during SSR dump
|  |  | 5m |  |  | Upload Inertial Maneuver ATS | 3 | [6 empty] | Can be done during SSR dump
|  |  | 10m |  |  | Upload Contact ATS | [7 empty] | Can be done during SSR dump
|  |  | 5m |  |  | Set SCB Clock | [7 empty] | CAN NOT be done during SSR dump
| 0505 | 1:05 |  |  |  | Repointing Contact LOS : AK
2011-06-05 | 0821 |  |  |  |  | Perigee |  | 3
|  |  |  | MOC |  | Queue contingency commands
2011-06-05 | 0845 | 4:45 | 90m |  |  | Repointing contact AOS : AUS, 64k |  | 3a |  |  |  |  | > 40 ksps
| 0900 | 5:00 | 25m |  |  | Repoint | 4 | [5 empty] | Housekeeping
|  |  | 25m |  |  | SSR Dump (if not possible on earlier pass) | [7 empty] | can be done while repointing - standard ops
|  |  | 5m |  |  | Verify Sun Angle & EPS Performance | 5 | [7 empty] | OP31303
|  |  | 2m |  |  | Reduce High Rate EPS TLM | 6 | [7 empty] | OP31418
|  |  | 2m |  |  | Delete Back Orbit Star Tracker TLM | 7 | [7 empty] | OP31416
| 1015 | 6:15 |  |  |  | Repointing Contact LOS : AUS
|  |  |  | FDG |  | FDG Pointing Check
|  |  |  | SYS |  | Repoint Maneuver Success Criteria
| 1030 | 6:30 |  | FDG |  | Repoint Correction yarget Vector if needed
| 11:00 | 7:00 |  | MOC |  | Repoint Correction ATS if needed
|  |  |  | All |  | Repoint Correction ATS approval if needed
EPS, ACS, SYS approval to proceed to Spin Up
2011-06-05 | 1200 | 8:00 | 90m |  |  | Contact AOS - AUS, 64k |  | 7a
|  |  | 10m |  |  | Upload Repoint Correction ATS if needed | [7 empty] | if no additional repoint needed, skip to Step 8, CEU OFF
|  |  | 5m |  |  | Repoint Correction if needed
|  |  | 5m |  |  | SSR Dump | 8
|  |  | 2m |  |  | CEU Off | 8
|  |  | 5m |  |  | Set 22rpm Limits | 9
|  |  | 15m |  |  | Star Tracker Off | 10 | [7 empty] | OP31202
|  |  | 5m |  |  | Upload Spin Up ATS | 11
| 1330 | 9:30 |  |  |  | Contact LOS
|  |  |  | MOC |  | Queue contingency commands | 12
2011-06-05 | 1515 | 11:15 | 60m |  |  | Spin Up Contact AOS - AUS, 64k |  | 12a
| 1530 | 11:30 | 4m |  |  | Spin Up | 13
[6 empty] | Enable Spin Rate Limits | 14 | [7 empty] | OP31203
| 1615 | 12:15 |  |  |  | Spin Up Contact LOS
2011-06-05 | 1715 | 13:15 | 60m |  |  | Back up Spin Up Contact AOS - AUS |  | 14a
| 1815 | 14:15 |  |  |  | Back up Spin Up Contact LOS
|  |  |  | HPS |  | Update Fuel Usage Table
|  |  |  | SYS |  | Spin Up maneuver Success Criteria
|  |  |  | FDG |  | Current OD Uncertainty (thru ADV1)
|  |  |  | FDG |  | Ground Station Viewperiod (thru ADV1)
|  |  |  | FDG |  | Star tracker Outages (thru ADV1)
|  |  |  | MOC |  | Station Antenna Predicts
|  |  |  | MOC |  | Confirmation of USN coverage for ADV1
|  |  |  | MOM |  | Time of ADV1
|  |  |  | MOM |  | Duration of Burn
|  |  |  | MOC |  | ADV1 ATS
|  |  |  | MOC |  | Contact ATS
|  |  |  | All |  | ADV1 ATS approval
2011-06-06 | 0430 |  |  |  |  | APL view begin
2011-06-06 | 0900 |  |  |  |  | HAW view begin
2011-06-06 | 1000 | 6:00 | 60m |  |  | Contact AOS : HAW01, 40k |  | 29a
| 1100 | 7:00 |  |  |  | Contact LOS
|  |  |  | ACS |  | ACS TLM assessment
|  |  |  | HPS |  | HPS TLM assessment
|  |  |  | EPS |  | EPS TLM assessment
|  |  |  | SYS |  | SCB TLM assessment, Temp plots
|  |  |  | All |  | All MAC products on SFTP
2011-06-06 | 1400 | 10:00 |  |  |  | Pre-ADV1 MAC
2011-06-06 | 1423 |  |  |  |  | AUS view Begin
2011-06-06 | 1700 | 13:00 | 60m |  |  | Contact AOS : AUS, 40k |  | 33a
|  |  | 5m |  |  | Reduce TLM Rates for Delta-V Burns | 15
|  |  | 5m | MOC |  | Upload ADV1 ATS | 16
| 1800 |  |  |  |  | Contact LOS
2011-06-07 | 0222 |  |  |  |  | AUS view End
| 0430 |  |  |  |  | APL view Begin
| 0920 |  |  |  |  | HAW view begin
| 1010 |  |  |  |  | AK view begin
| 1500 |  |  |  |  | AUS view Begin
2011-06-07 | 1845 | 14:45 | 60m |  |  | Contact AOS : HAW01, 2k |  | 43a
|  |  |  | MOC |  | Backup Upload ADV1 ATS | 16
Set SCB Clock
| 1945 |  |  |  |  | Contact LOS
2011-06-08 | 0230 |  |  |  |  | AUS view End
| 0430 |  |  |  |  | APL view Begin
2011-06-08 | 0700 | 3:00 | 60m |  |  | APL Contact AOS - Pre ADV1 SOH, 64k |  | 46a
| 0800 | 4:00 |  |  |  | APL Contact LOS
| 0920 |  |  |  |  | HAW, AK view begin
2011-06-08 | 1500 |  |  |  |  | APL view Ends, AUS begin
2011-06-08 | 1745 | 13:45 | 30m |  |  | Contact AOS : HAW01, 2k |  | 47a
|  |  |  | SYS |  | Verify Heater Setpoints | 17
| 1815 |  |  |  |  | Contact LOS
|  |  |  | MOC |  | Queue contingency commands | 18
2011-06-08 | 1945 | 15:45 | 90m |  |  | ADV1 Contact AOS : HAW01, 2k |  | 47a
| 2000 | 16:00 | 10m |  |  | ADV1 | 18 | [6 empty] | HAW view ends before set contact time end
| 2115 | 17:15 |  |  |  | ADV1 Contact LOS
| 2130 | 17:30 |  | HPS |  | Update Fuel Usage Table
| 2130 | 17:30 |  | SYS |  | ADV1 maneuver Success Criteria
| 2200 | 18:00 |  | SYS |  | Place Updates on SFTP
| 2200 | 18:00 |  | MT |  | Send updates to Steve Green
| 2300 | 19:00 | 60m | SG |  | Change in tank pressure & propellant consumption in ADV1
| 2400 | 20:00 | 30m | MT |  | ADV1 Burn Reconstruction New Delta-V based on observed pressure Comparison to Previous Delta-V
2011-06-09 | 0235 |  |  |  |  | AUS view end
2011-06-09 | 0445 |  |  |  |  | Apogee |  | 47
2011-06-09 | 0530 | 1:30 | 60m |  |  | APL Contact AOS - Post ADV1 FC Dump, 64k |  | 47d
| 0630 | 2:30 |  |  |  | APL Contact LOS
| 0920 |  |  |  |  | HAW, AK view begin
2011-06-09 | 1200 | 8:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47d
[6 empty] | Enable Back Orbit Buffer TLM if FC Dump successful | 19
| 1300 | 9:00 |  |  |  | Contact LOS
2011-06-09 | 1600 |  |  |  |  | AUS view begin
| 2040 |  |  |  |  | HAW, AK view end
2011-06-10 | 0240 |  |  |  |  | AUS view End
| 0430 |  |  |  |  | APL view Begin
2011-06-10 | 0545 | 1:45 | 60m |  |  | APL Contact AOS - FC Dump, 64k |  | 46d
| 0645 | 2:45 |  |  |  | APL Contact LOS
| 0900 |  |  |  |  | AK view begin
| 1000 |  |  |  |  | HAW view begin
2011-06-10 | 1330 | 9:30 | 60m |  |  | Contact AOS : HAW01,2k |  | 44d | [5 empty] | Last contact before null
[6 empty] | Enable Back Orbit Buffer TLM if FC Dump successful | 19
| 1430 | 10:30 |  |  |  | Contact LOS
2011-06-10 | 1500 | 11:00 |  | SYS |  | Expected ADV2 initial pressure, temperature, propellant mass
| 1500 | 11:00 |  | SYS |  | Expected ADV3 initial temperature,
| 1500 | 11:00 |  | SYS |  | Place Updates on SFTP
| 1530 | 11:30 |  | MT |  | Send updates to Steve Green
AUS view begin
| 1730 | 13:30 | 2h | SG |  | Expected ADV2 & ADV3 mass flow rate & pressure curves
| 2200 |  |  |  |  | HAW, AK view end
2011-06-11 | 0250 |  |  |  |  | AUS view end
2011-06-12 | 1400 | 10:00 | 45m | MT |  | Generate thrust & delta-V as a function of new model predictions | [7 empty] | drop dead time for this input to FDG
2011-06-12 | 1500 | 11:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 19d | [5 empty] | First contact after null
| 1600 | 12:00 |  |  |  | Contact LOS
| 1700 |  |  |  |  | APL view 1700-2030
| 2130 |  |  |  |  | AUS view begin
2011-06-13 | 0130 | 21:30 | 60m |  |  | Contact AOS : AK, 160k |  | 8d
|  |  |  | MOC |  | FC Dump
| 0230 | 22:30 |  |  |  | Contact LOS
2011-06-13 | 0330 | 23:30 |  | SYS |  | Revised estimate : Expected ADV2 initial pressure, temperature, propellant mass
| 0330 | 23:30 |  | SYS |  | Revised estimate : Expected ADV3 initial temperature
| 0330 | 23:30 |  | SYS |  | Place Updates on SFTP
| 0400 | 0:00 |  | MT |  | Send updates to Steve Green
| 0430 | 0:30 |  | FDG |  | Preliminary Burn Plan (Internal)
2011-06-13 | 0545 |  |  |  |  | Perigee
| 0600 | 2:00 | 2h | SG |  | Expected ADV2 & ADV3 mass flow rate & pressure curves
| 0600 | 2:00 |  | MOM |  | ADV2 duration & time based on prelim burn plan (not including OD)
| 0600 | 2:00 |  | MOM |  | ADV3 duration & time based on prelim burn plan (not including OD)
| 0700 | 3:00 | 45m | MT |  | Generate thrust & delta-V as a function of new model predictions
2011-06-13 | 1100 | 7:00 | 60m |  |  | Contact AOS : HAW01, 64k |  | 9a
| 1200 | 8:00 |  |  |  | Contact LOS
2011-06-13 | 13:30 | 9:30 | 60m |  |  | Contact AOS : AUS, 40k |  | 12a
| 14:30 | 10:30 |  |  |  | Contact LOS
| 1620 |  |  |  |  | HAW view end
| 1800 | 14:00 |  | FDG |  | Dry mass + fuel mass = total mass (wet mass) assumptions going into ADV2 & 3 (parroting)
| 1800 | 14:00 |  | FDG |  | ADV1 Performance Assessment (thrust scale factor)
| 1800 | 14:00 |  | FDG |  | Current OD Uncertainty
| 1800 | 14:00 |  | FDG |  | Target Orbit Period Uncertainty (Napoleon plot)
| 1800 | 14:00 |  | FDG |  | No Additional Delta-V Burn Trajectory (immediate effects, not long term effects)
| 1800 | 14:00 |  | FDG |  | Apogee & Perigee Times (burn & no-burn)
| 1800 | 14:00 |  | FDG |  | Crossing Times
| 1800 | 14:00 |  | FDG |  | Viewperiods Report (burn & no-burn)
| 1800 | 14:00 |  | FDG |  | Duration of ADV3 Burn - based on analysis
| 1800 | 14:00 |  | FDG |  | Final FDG Burn Plan delivery
| 2000 | 16:00 |  | MOC |  | SAP
| 2000 | 16:00 |  | MOC |  | ADV2 ATS on SFTP
| 2000 | 16:00 |  | MOC |  | ADV3 ATS on SFTP
| 2000 | 16:00 |  | MOC |  | Contact ATS on SFTP
2011-06-14 | 0100 |  |  |  |  | AUS view ends
| 0400 |  |  |  |  | APL view begin
| 0800 |  |  |  |  | HAW view begin
| 1200 | 8:00 |  | All |  | Approve ADV2 ATS
| 1200 | 8:00 |  | All |  | Approve ADV3 ATS
| 1200 | 8:00 |  | All |  | Approve Contact ATS
| 1200 | 8:00 |  | ACS |  | ACS TLM assessment
| 1200 | 8:00 |  | HPS |  | HPS TLM assessment
| 1200 | 8:00 |  | EPS |  | EPS TLM assessment
| 1200 | 8:00 |  | SYS |  | SCB TLM assessment, Temp plots
| 1200 | 8:00 |  | All |  | All MAC products on SFTP
| 1400 | 10:00 | 2h |  |  | Pre-ADV2 MAC
2011-06-14 | 1600 | 12:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 33a
| 1700 | 13:00 |  |  |  | Contact LOS
2011-06-14 | 1900 | 14:00 | 60m |  |  | Contact AOS : AUS, 2k |  | 34a | [5 empty] | comment says 40k, but too high
|  |  | 2m |  |  | Timed Command to Disable Backorbit Buffer | 20
|  |  | 5m |  |  | Upload ADV2 ATS | 21
|  |  | 5m |  |  | Upload ADV3 ATS | 21
| 2000 | 15:00 |  |  |  | Contact LOS
2011-06-15 | 0145 |  |  |  |  | AUS view ends
| 0400 |  |  |  |  | APL view begin
2011-06-15 | 0915 | 5:15 | 60m |  |  | Contact AOS : HAW01, 2k, ADV2,3 Upload Backup |  | 40a
|  |  | 5m |  |  | Set SCB Clock
| 1015 | 6:15 |  |  |  | Contact LOS
| 1345 |  |  |  |  | APL view end, AUS view begin
| 1730 |  |  |  |  | AK view end
| 1930 |  |  |  |  | HAW view end
2011-06-16 | 0145 |  |  |  |  | AUS view ends
2011-06-16 | 0445 | 0:45 | 60m |  |  | APL Contact AOS - Pre ADV2 FC Dump, 64k |  | 45a
| 0545 | 1:45 |  |  |  | APL Contact LOS
| 0900 |  |  |  |  | HAW, AK view begin
| 1430 |  |  |  |  | APL view end, AUS view begin
2011-06-16 | 1630 | 12:30 | 30m |  |  | Contact AOS : HAW01,2k, ADV2,3 Upload Backup |  | 47a
[6 empty] | Verify Heater Setpoints | 22
| 1700 | 13:00 |  |  |  | Contact LOS
|  |  |  | MOC |  | Queue contingency commands | 23
2011-06-16 | 1845 | 14:45 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47a
| 1900 | 15:00 | 10m |  |  | ADV2 | 23
| 1945 | 15:45 |  |  |  | Contact LOS
| 2015 | 16:15 |  | HPS |  | Update Fuel Usage Table
| 2015 | 16:15 |  | SYS |  | ADV2 maneuver Success Criteria
| 2015 | 16:15 |  | SYS |  | Place Updates on SFTP
If everything within limits skip to Pre-ADV3 MAC
| 2030 | 16:30 |  | MT |  | Send updates to Steve Green
| 2130 | 17:30 | 60m | SG |  | Change in tank pressure & propellant consumption in ADV2
| 2200 | 18:00 | 30m | MT |  | ADV2 Burn Reconstruction New Delta-V based on observed pressure Comparison to Previous Delta-V
|  |  |  | FDG |  | Reconstruct ADV2, Predict Orbit Period and Uncertainty at A3
| 2300 | 19:00 |  | SG |  | Expected ADV3 mass flow rate & pressure curves
| 2400 | 20:00 |  | MT |  | Generate thrust & delta-V as a function of new model predictions
|  |  |  | FDG |  | Use Reconstructed ADV2 and updated predicted ADV3 using commanded duration to predict Orbit Period and uncertainty at A3
|  |  |  | FDG |  | Generate Napoleon Plot
|  |  |  | FDG |  | Retarget and calculate new ADV3 Duration (Ideal duration?)
| 0200 |  |  |  |  | AUS view end
| 0400 |  |  |  |  | APL view begin
2011-06-17 | 0445 | 0:45 | 60m |  |  | APL Contact AOS - Post ADV2 FC Dump,64k |  | 47a
| 0545 | 1:45 |  |  |  | APL Contact LOS
|  |  |  | ACS |  | ACS TLM assessment
|  |  |  | HPS |  | HPS TLM assessment
|  |  |  | EPS |  | EPS TLM assessment
|  |  |  | SYS |  | SCB TLM assessment, Temp plots
|  |  |  | All |  | All MAC products on SFTP
2011-06-17 | 0600 |  |  |  |  | Apogee |  | 47
| 0630 | 2:30 | 30m | MOC |  | Generate ADV3 Modification CAR
| 0730 | 3:30 | 60m | All |  | Approve ADV3 Modification CAR
| 0800 | 4:00 | 1h |  |  | Pre-ADV3 MAC
| 0900 |  |  |  |  | HAW, AK view begin
|  |  |  | MOC |  | Queue contingency commands | 25
2011-06-17 | 1010 | 6:10 | 90m |  |  | Contact AOS : HAW01, 2k |  | 47d
|  |  |  | MOC |  | Upload ADV3 Updates (if needed)
|  |  |  | SYS |  | Verify Heater Setpoints | 24
| 1100 | 7:00 | 10m |  |  | ADV3 | 25
| 1140 | 7:40 |  |  |  | Contact LOS
2011-06-17 | 1200 | 0:45 | 60m |  |  | APL Contact AOS - Post ADV3 FC Dump, 64k |  | 47d | [5 empty] | Need to move this contact later - STX violation - mirror 1800 pass?
| 1300 | 1:45 |  |  |  | APL Contact LOS
| 1430 | 10:30 |  | HPS |  | Update Fuel Usage Table
| 1430 | 10:30 |  | SYS |  | ADV3 maneuver Success Criteria
| 1430 | 10:30 |  | SYS |  | Place Updates on SFTP
| 1530 |  |  |  |  | AUS view begin
2011-06-17 | 1800 | 14:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47d
[6 empty] | Enable Back Orbit Buffer TLM if FC Dump successful | 26
| 1900 | 15:00 |  |  |  | Contact LOS
| 0220 |  |  |  |  | AUS view end
2011-06-18 | 0400 |  |  |  |  | APL view begin
| 0900 |  |  |  |  | HAW, AK view end
2011-06-18 | 1400 | 10:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 44d
| 1500 | 11:00 |  |  |  | Contact LOS
| 1500 |  |  |  |  | View end
2011-06-20 | 1230 |  |  |  |  | HAW, AK, APL view begin
2011-06-20 | 1500 | 11:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 25d
| 1600 | 12:00 |  |  |  | Contact LOS
| 2000 |  |  |  |  | APLview end; AUS view begin
| 0110 |  |  |  |  | HAW view end
2011-06-21 | 0300 |  | 60m |  |  | Contact AOS : AUS, 2k |  | 16d
| 0400 | 0:00 |  |  |  | Contact LOS
2011-06-21 | 0530 | 1:30 | 60m |  |  | Contact AOS : AK, 40k |  | 14d
FC Dump
| 0630 | 2:30 |  |  |  | Contact LOS
| 0900 |  |  |  |  | APLview 0900 - 1120
| 1110 |  |  |  |  | AK view end
2011-06-21 | 1624 |  |  |  |  | Perigee
|  |  |  | FDG |  | ADV3 Performance Assessment (% delta-V acheived)
|  |  |  | FDG |  | TCM recommendation | 27
|  |  |  | FDG |  | Target Orbit Period Uncertainty (Napoleon plot)
|  |  |  | FDG |  | Helionose Progression (long term)
|  |  |  | FDG |  | Apogee Radius (long term)
|  |  |  | FDG |  | Perigee Radius (long term)
|  |  |  | FDG |  | Communications Analysis
|  |  |  | FDG |  | Apogee & Perigee Times (long term)
|  |  |  | FDG |  | Crossing Times (long term)
|  |  |  | FDG |  | Star Tracker Outages (long term)
|  |  |  | FDG |  | Viewperiods Report (long term)
|  |  |  | MOC |  | USN Coverage for Spin Down
|  |  |  | MOC |  | USN Coverage after Spin-Down
|  |  |  | MOC |  | USN Coverage for Repointing
| 2030 |  |  |  |  | APLview 6/20 2030- 6/21 0430
2011-06-22 | 0630 | 2:30 | 60m |  |  | Contact AOS : HA, 40k |  | 17a
FC Dump
| 0730 | 3:30 |  |  |  | Contact LOS
| 0700 | 3:00 | 30m | FDG |  | Repointing Target Vector
| 0800 | 4:00 |  | MOC |  | SAP
| 0800 | 4:00 | 60m | MOC |  | Spin Down ATS on SFTP
| 0900 | 5:00 | 60m | MOC |  | Repointing ATS on SFTP
| 1000 | 6:00 | 60m | MOC |  | Contact ATS on SFTP
| 1000 | 6:00 | 60m | All |  | Approve Spin Down ATS (prior to MAC)
| 1000 | 6:00 | 60m | All |  | Approve Repointing ATS (prior to MAC)
| 1100 | 7:00 |  | All |  | Approve Contact ATS (prior to MAC)
2011-06-22 | 1200 | 8:00 | 60m |  |  | Contact AOS : AUS, 40k |  | 21a
|  |  | 5m |  |  | Restore nominal TLM rates | 33
| 1300 | 9:00 |  |  |  | Contact LOS
| 1400 | 10:00 |  | ACS |  | ACS TLM assessment
| 1400 | 10:00 |  | HPS |  | HPS TLM assessment
| 1400 | 10:00 |  | EPS |  | EPS TLM assessment
| 1400 | 10:00 |  | SYS |  | SCB TLM assessment, Temp plots
| 1400 | 10:00 |  | All |  | All MAC products on SFTP
| 1500 | 11:00 | 2h |  |  | Pre-Spin Down MAC
| 1600 |  |  |  |  | HAW view end
2011-06-23 | 0030 |  |  |  |  | AUS view end
| 0330 |  |  |  |  | APL view begin
2011-06-23 | 0800 |  | 60m |  |  | Contact AOS |  | 31a
|  |  | 5m |  |  | Upload Spin Down ATS | 35
| 0900 |  |  |  |  | Contact LOS
|  |  |  | MOC |  | Queue contingency commands | 36
2011-06-24 | 0815 | 4:45 | 90m |  |  | Contact AOS : HAW01, 2k |  | 42a
|  |  | 10m |  |  | Set Gyro as Low Rate Sensor | 34 | [7 empty] | OP31206
| 0900 | 5:00 | 30m |  |  | Spin Down to 4rpm | 37
|  |  | 5m |  |  | Enable Spin Rate FDC | 38 | [7 empty] | OP31203
|  |  | 5m |  |  | Set Accelerometer as Low Rate Sensor | 39 | [7 empty] | OP31206
| 0945 | 5:45 |  |  |  | Contact LOS
|  |  |  | HPS |  | Update Fuel Usage Table
|  |  |  | SYS |  | Spin Down Maneuver Success Criteria
EPS, ACS, SYS approval to proceed to Repoint
| 1130 |  |  |  |  | APL view end
| 1230 |  |  |  |  | AUS view end
| 1750 |  |  |  |  | HAW view end
2011-06-24 | 0100 |  |  |  |  | AUS view end
| 0330 |  |  |  |  | APL view begin
| 0800 |  |  |  |  | HAW view begin
| 0930 |  |  |  |  | AK view begin
2011-06-24 | 1200 | 9:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 43a
|  |  | 15m |  |  | Star Tracker On | 40 | [7 empty] | OP31202
[6 empty] | Upload Repointing ATS | 41
| 1300 | 9:00 |  |  |  | Contact LOS
|  |  |  | MOC |  | Queue contingency commands | 42
2011-06-24 | 1515 | 11:15 | 60m |  |  | Contact AOS : HAW01, 2k |  | 44a
| 1530 | 11:30 | 35m |  |  | Repoint | 42
|  |  | 5m |  |  | Set limits for 4rpm | 43
|  |  | 5m |  |  | Verify Static Z Rate | 44
|  |  | 2m |  |  | Enter Science State | 45
| 1615 | 12:15 |  |  |  | Contact LOS
2011-06-24 | 1730 | 13:30 | 60m |  |  | Contact AOS : HAW01, 2k |  | 44a
[6 empty] | Increase Battery TLM | 46 | [7 empty] | OP31418
[6 empty] | Add Star Tracker Attitude to Backorbit TLM | 47
[6 empty] | CEU ON | 48
| 1830 | 14:30 |  |  |  | Contact LOS
2011-06-25 | 0120 |  |  |  |  | AUS view end
| 0330 |  |  |  |  | APL view begin
| 0820 |  |  |  |  | HAW, AK view begin
2011-06-25 | 1000 | 6:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47a
|  |  | 10m |  |  | LV Checkout | 49
[6 empty] | Upload Hi Diagnostics | 50
[6 empty] | Set Payload Limits | 51
| 1100 | 7:00 |  |  |  | Contact LOS
2011-06-25 | 1315 | 9:15 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47a
|  |  | 30m |  |  | OFF_TO_HVSTANDBY macros | 52
| 14:00 | 10:00 |  |  |  | Contact LOS
| 14:00 | 10:00 | 60m |  |  | Return to Science MAC
2011-06-25 | 1500 | 11:00 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47a
|  |  | 5m |  |  | Upload o130 ATS | 53
|  |  | 5m |  |  | Upload o131 ATS | 53
|  |  | 25m |  |  | ASCENDING macros | 54
| 1600 | 12:00 |  |  |  | Contact LOS
2011-06-25 | 1730 | 13:30 | 60m |  |  | Contact AOS : HAW01, 2k |  | 47a
| 1830 | 14:30 |  |  |  | Contact LOS
| 1930 |  |  |  |  | HAW view end
2011-06-26 | 0301 |  |  |  |  | Apogee |  | 47
Note on B56: Michelle Reno: Changed burn time to allow more time for repointing verification & spin-up upload